## Product_Backlog
Backlog ID | Epic | User Story | Priority | Story Points | Acceptance Criteria | Sprint | Status
US-001 | Data Foundation & Quality | As a Program Manager, I want student, academic, support, faculty and feedback data consolidated into a structured data model so that program performance can be monitored from a centralized source. | High | 8 | All required project datasets are consolidated into a centralized data source, key IDs and data types are validated, required table relationships are established, and the resulting model is ready for KPI reporting and analysis. | Sprint 1 | Done
US-002 | Data Foundation & Quality | As a Program Manager, I want the project data validated for completeness, consistency, and accuracy so that management KPIs and dashboard insights are reliable. | High | 8 | Required datasets contain no critical missing or duplicate identifiers; key values and business rules are validated; relationships between student, faculty, academic and support data are consistent; and the validated data is suitable for dashboard reporting. | Sprint 1 | Done
US-003 | Data Foundation & Quality | As a Program Manager, I want related project datasets connected through a structured analytical data model so that KPIs can be analyzed consistently across students, programs and operational areas. | Medium | 5 | Required datasets are connected using appropriate relationships; student-level tables can be analyzed consistently through the central student data; faculty relationships support relevant academic analysis; and filtering produces consistent results across related dashboard metrics. | Sprint 1 | Done
US-004 | Student Success Analytics | As a Program Manager, I want to monitor key student-success indicators such as attendance, pass rate, course completion, and assignment submission so that I can assess overall program performance and identify areas requiring attention. | High | 8 | Dashboard displays accurate Attendance %, Pass Rate %, Course Completion %, and Assignment Submission %; KPIs respond correctly to Program and Semester filters; and results are consistent with the validated source data. | Sprint 2 | Done
US-005 | Student Success Analytics | As a Program Manager, I want to identify and monitor at-risk students so that academic and support teams can prioritize students requiring intervention. | High | 8 | High-risk students are accurately identified using the defined risk classification; the dashboard displays the at-risk student count; results can be analyzed by Program and Semester; and the information supports prioritization for academic or support intervention | Sprint 2 | Done
US-006 | Student Success Analytics | As a Program Manager, I want to compare student-success performance across programs and semesters so that I can identify performance gaps and areas requiring management attention. | Medium | 8 | Student-success KPIs can be compared across programs and semesters; Program and Semester filters update relevant visuals correctly; differences in attendance, pass rate, assignment submission and course completion can be identified; and displayed results are consistent with validated data. | Sprint 2 | Done
US-007 | Issue & SLA Management | As a Program Manager, I want to monitor student-support issues and unresolved ticket backlog so that operational bottlenecks can be identified and prioritized for resolution. | High | 8 | Total and unresolved support issues are accurately displayed; issue volumes can be analyzed by category and assigned team; open-ticket calculations are consistent with the source data; and the dashboard enables identification of areas with significant operational backlog. | Sprint 2 | Done
US-008 | Issue & SLA Management | As a Program Manager, I want to monitor SLA compliance and resolution turnaround time so that service-performance gaps can be identified and corrective actions can be prioritized. | High | 8 | SLA Compliance % and Average Resolution TAT are calculated accurately; SLA performance can be analyzed by assigned team; breached or underperforming areas can be identified; and dashboard results are consistent with the defined SLA and resolution logic. | Sprint 2 | Done
US-009 | Issue & SLA Management | As a Program Manager, I want to analyze support issues by category and assigned team so that recurring problem areas and operational improvement opportunities can be identified. | Medium | 5 | Support issues can be analyzed by issue category and assigned team; issue volumes and service-performance differences are visible; recurring or high-volume problem areas can be identified; and results respond correctly to applicable dashboard filters. | Sprint 2 | Done
US-010 | Student Experience Analytics | As a Program Manager, I want to monitor and analyze student feedback so that I can understand the overall student experience and identify areas requiring improvement. | High | 8 | Average student feedback rating is calculated accurately; feedback can be analyzed by category and program; areas with comparatively lower ratings can be identified; applicable filters update the analysis correctly; and results support identification of student-experience improvement opportunities. | Sprint 2 | Done
US-011 | Student Experience Analytics | As a Program Manager, I want to compare feedback across categories and programs so that recurring student-experience concerns can be identified and prioritized for improvement. | Low | 3 | Feedback ratings can be compared across categories and programs; comparatively lower-rated areas can be identified; applicable filters update the analysis correctly; and the analysis supports identification of recurring student-experience concerns. | Sprint 2 | Done
US-012 | Program Governance & Management Insights | As a Program Manager, I want to track and manage program risks and issues so that potential threats are mitigated and active problems are addressed before they significantly affect program outcomes. | High | 8 | Program risks and issues are documented with appropriate ownership, probability, impact, priority and status; mitigation or corrective actions are defined; and the register enables ongoing monitoring and management of significant program concerns. | Sprint 3 | Done
US-013 | Program Governance & Management Insights | As a Program Manager, I want to translate dashboard findings into management insights and recommended actions so that identified performance and operational gaps can be addressed through data-driven decisions. | Medium | 5 | Key findings from student-success, operational and student-experience analytics are identified; significant performance gaps are translated into management insights; appropriate actions are recommended with clear areas of focus; and recommendations are supported by relevant dashboard KPIs. | Sprint 3 | Done
US-014 | Program Governance & Management Insights | As a Program Manager, I want project deliverables, decisions, and outcomes documented in a structured portfolio package so that the project can be reviewed, communicated, and formally closed. | Low | 5 | Key project deliverables are organized and documented; major decisions, outcomes and management insights are captured; supporting dashboard and PM artifacts are included; and the final project package is suitable for review, portfolio presentation and project closure. | Sprint 3 | Done