## Sheet1
EdSuccess Analytics — Risk & Issue Register
EdTech Student Success and Program Management Analytics
ID | Type | Risk / Issue Description | Category | Probability | Impact | Priority | Owner | Mitigation / Action Plan | Status | Target Date | Resolution / Remarks
R-001 | Risk | Inconsistent student data may affect KPI accuracy | Data Quality | Medium | High | High | Data & BI Team | Validate source data and perform quality checks before reporting | Open | — | —
R-002 | Risk | Changes in data structure may break dashboard relationships or measures | Technical | Medium | High | High | Data & BI Team | Maintain standardized schemas and test changes before refresh | Monitoring | — | —
I-001 | Issue | High number of unresolved student-support tickets | Operations | — | High | High | Student Support Team | Prioritize backlog by severity and SLA status | In Progress | — | Review backlog weekly
I-002 | Issue | SLA compliance is below the desired operational level | SLA / Operations | — | High | Critical | Program Manager | Analyze breaches by team/category and implement corrective actions | In Progress | — | Track through dashboard
R-003 | Risk | Limited historical data may restrict trend and forecasting analysis | Data Quality | High | Medium | High | Program Manager | Document current data limitations and plan historical data expansion for future phases | Open | — | —
R-004 | Risk | High student-risk levels may require more intervention capacity than available | Student Success | Medium | High | High | Program Manager | Prioritize students using attendance, completion and performance indicators and coordinate targeted interventions | Monitoring | — | Review risk indicators regularly
I-003 | Issue | Assignment submission rate is below the desired engagement level | Academic / Engagement | — | High | High | Academic Team | Identify low-submission student groups and coordinate faculty follow-up and reminders | Open | — | Monitor submission rate through dashboard
I-004 | Issue | A substantial number of students are currently classified as high risk | Student Success | — | High | Critical | Program Manager | Segment high-risk students, identify contributing factors and coordinate targeted academic/support interventions | In Progress | — | Review during program performance meetings
Open → identified, action still required
Monitoring → actively watching/managing it
In Progress → corrective/mitigation work is currently happening
Mitigated → risk has been reduced through action
Resolved → issue has been fixed
Closed → no further action or tracking is required